## Sheet1
|  |  | Who | Time and | Cost | Work in | Chore/purch.
|  |  | responsible | date |  | progress | Complete
Mease - Bell Ringing |  |  | Gardner | Sat. noon | N/A |  | x | Set - Mease confirmed to Gardner
Plaque dedication |  |  | All | Sat. noon | N/A
Purchase Plaques |  |  | Gardner | Fri,Sat, Sun | N/A | x | x
Souvenirs - mini plaques |  |  | Gardner/Lilley | Fri,Sat, Sun | N/A | x | x
Plaque Hanging |  |  | Neddo, plus | July 7th - 12th | N/A |  |  | Need to set a time (2pm?)
Camp Clearing |  |  | Glancy, plus | week before | N/A | x |  | Has anyone heard from her lately?
Signs for Camp special spots |  |  | Neddo, Wyatt, Poulson | July 7th - 12th | 60
Signs for Friday social |  |  | All committee plus | Friday day | 50
Caterer Friday |  |  | Neddo | Fri. 7:00 | 600 | x |  | est. 200.00 over food cost
Caterer Saturday |  |  | Gardner | Sat. 4:00 | 600 | x |  | Could be more | JR comfirmed. Need to ask H/F Club to set up tables in Lodge and comfirm use of grill.
Caterer Sunday |  |  | Neddo | Sun. 1:00 | 1300 | x
Souvenirs - Dirt |  |  | Gardner - Neddo | When possible | N/A | x | x | Gardner will hand out on Fri.
Souvenirs - Coozies |  |  | Neddo | Fri, Sat, Sun | N/A | x | x
T-Shirts |  |  | Neddo | Fri, Sat, Sun | N/A | x
First Aid Kits - 2 |  |  | Neddo-1, purch - 1 | Sat, Sun | 22 | x | x
Notify Gallahd/H&F Lodge,staying over |  |  | Neddo, Wyatt, Poulson | Sat | N/A |  |  | Confirm we can use Lodge for meal
Chck Radios between Gal. & camp site |  |  | Neddo, Wyatt, Poulson | Thurs. July 12 | N/A
Beans |  |  | Wyatt | Sat | N/A
Directions to Camp |  |  | Lilley | Friday night | N/A |  |  | Do I need to pick up balloons, markers, cardboard, duct tape etc. when I get to Charleston? -- Bob | Arrange meeting location for Sat morning to lead folks out to camp.
Children's Crafts |  |  | Neddo | Sat | N/A | x
FOP (fallback on Saturday) |  |  | Neddo | Sat | N/A | x | x
Registration online |  |  | Lilley | ASAP | N/A | x | x
Composit of t-shirts for online |  |  | Neddo | ASAP | N/A | x | x
Keg for Friday night |  |  | Neddo | week before | 120
Ad in retirees paper |  |  | Wyatt | May - June
Check PayPal info. For bank |  |  | Neddo | ASAP | $14.00 / trans. | x | x
Get Coonskin reservation |  |  | Neddo | ASAP | 75 | x | x
Pick up Wings Friday evening |  |  | Gardner | Fri. 6:00pm | 200 for 76.00
Lemonade dispenser for Weekend |  |  | Neddo | Friday | 20
Drinks for entire weekend |  |  | Neddo | When we get fri food | 150
Guestbook - who has it? |  |  | Someone to be at door | Fri. Sat. Sun. | Should have one |  |  | We'll need Fri help w/shirts & walk-in registrations, etc.
3139
|  |  |  | Wyatt Contribution | 1000
|  |  |  | Lilley Contribution | 300
|  |  |  | Balance in Checkbook | 408.43
|  |  |  | Total needed to collect | 1430.57 |  |  | Barb: Am I right that this does not include shirts at all? So any profit from shirts will help. I have $1332.13+ in the bank, but that is for shirts plus registration. I think I had 22 people at $40 so far for registration (not including you and me; so that's about $880 + 160 = $1,040, plus Dave? Mease? and hopefully others!)
DRINKS FOR WEEKEND
Case count | # of cases | Description | Cost/case | ext. cost | How many
1= 15 ct. | 3 | Tradewinds ice tea | 9.88 | 29.64 | 45
1 = 12 ct | 1 | Orange soda | 2.98 | 2.98 | 12
1 = 24 ct. | 2 | Sprite | 9.48 | 18.96 | 48
1 = 24ct. | 1 | Diet Sprite | 9.48 | 9.48 | 24
1 = 32 ct. | 3 | Diet Coke | 9.98 | 29.94 | 96
1 = 32ct. | 2 | Reg. Coke | 9.98 | 19.96 | 64
1 = 24ct. | 1 | Dr. Pepper | 7.48 | 7.48 | 24
1 = 48 ct. | 2 | Deer Park Water | 6.88 | 13.76 | 96
1 = 24 ct. | 1 | Diet Dr. Pepper | 7.48 | 7.48 | 24
|  |  |  | 139.68 | 433
|  |  | TAX | 8.3808
|  |  | TOTAL | 148.0608
Plus, I plan to have a large dispenser filled with lemonade.
FRIDAY NIGHT'S MEAL
Size | # to buy | Description | Cost per item | Ext. cost | Feed how many
Reg. size | 2 | Chip dip | 4 | 8
1 = 6lb. | 2 | Meatballs | 13.98 | 27.96 | 12 lb.
1 = 3lb. | 2 | Weenies | 9.18 | 18.36 | 6 lb.
1 = 4lb. | 3 | Veggie Tray | 9.98 | 29.94 | 8 lb.
1 serve 30 | 3 | Cheese Tray | 19.98 | 59.94 | 90
1 = 4lb. | 2 | Fruit Tray | 10.48 | 20.96 | 8 lb.
Sheet cake | 1 | Cake | 21 | 21
1 = 36ct | 3 | Bread rolls | 4.98 | 14.94 | 108
| 200 | Cold Spot Wings | 76 | 76 | 50 @ 4ea.
Large cont. | 1 | Salsa | 6.98 | 6.98
| 2 | Tortilla chips | 3 | 6
| 3 | Regular chips | 3 | 9
| 1 | bbq sauce/weenie | 10 | 10
100 | 1 | Plates | 10 | 10
100 | 1 | Spoons/forks | 20 | 20
100 | 1 | Napkins | 10 | 10
349.08
|  |  | TAXES | 20.9448
|  |  | TOTAL | 370.0248